## Agenda
Constructability & MOT Review Meeting Agenda Revised: 8/07/2024
FPN No: |  |  |  |  | Lump Sum |  |  | Pay Items |  |  |  |  | Date of Meeting:
Project Description: |  |  |  | Milling & Resurfacing and Pier Protection | [8 empty] | County:
Production Date: | [12 empty] | Letting Date:
Section: | [12 empty] | MP Range:
Checklist
New Construction/Widening: | [7 empty] | Yes | No |  |  | Recommend Black base * |  |  |  | Yes |  | No
RRR Mill & Resurface : | [7 empty] | Yes | No |  |  | If yes, Design Life = |  | ______________ |  |  | Other: ________
Widening (for RT/LT Turn Lane): | [7 empty] | Yes | No |  |  | Recommend Black base * |  |  |  | Yes |  | No
Widening (for U-Turn Lane): | [7 empty] | Yes | No |  |  | Recommend Black base * |  |  |  | Yes |  | No
Pavement Type Selection Report Required: | [7 empty] | Yes | No
Existing parabolic crown: | [7 empty] | Yes | No
Match existing pavement cross-slope: | [7 empty] | Yes | No
Overlay/cross-slope correction with milling operation: | [7 empty] | Yes | No
Generalized Traffic Level of Service:
|  |  | Posted Speed |  |  | mph | Truck Traffic % |  | 4 | [5 empty] | Varies
|  |  | Design Speed |  |  | mph | AADT |  |  |  | Accumulated ESAL's
Design Analysis/Pavement Deficiencies in Pavement Condition Survey:
|  | Asphalt Shoving/Rippling, Stripping, Other:_______________ | [7 empty] | Rutting |  |  |  |  | Cracking
Discussion/Provide Applicable Handouts (to be sent to all attendees one week prior to meeting)
1 - Proposed Pavement Design and back-up documentation
2 - Special Considerations for Performance Grade Binder or Pavement Type
3 - Pavement Type Selection Report (If applicable)
4 - Emergency Shoulder Use
5- Proposed Typical Section(s) and cross slopes
6 - Detail(s) of cross-slope correction for overbuild or milling depth
7 - Proposed Variation(s) if needed and need of Developmental Specifications
8 - MOT sequencing for Paving Operations and compatibility with other construction phasing
9 - MOT phases, Signs erection, and procurement conflicts
10 - TCP Concept Checked for Proper Accommodation of Pedestrians and Bicyclists
11 - Lane closure analysis with local considerations
12 - If an open cut is proposed, discuss considerations for Jack and Bore
Attendees: | [12 empty] | E-Mail
Dept. Project Manager:
Design Consultant Firm:
Consultant EOR:
Construction Project Administrator:
|  | Rebecca Plumlee, P.E. D5 Pavement Design Engineer | [10 empty] | rebecca.plumlee@dot.state.fl.us
|  | Angela Cardona, D5 Temporary Traffic Control Plans | [10 empty] | angela.cardona@dot.state.fl.us
|  | Stan Carroll, D5 Temporary Traffic Control Plans | [10 empty] | william.carroll@dot.state.fl.us
|  | Tim Keefe, E.I. D5 District Materials & Research | [10 empty] | timothy.keefe@dot.state.fl.us
|  | D5 Construction-Design Coordination Group | [10 empty] | D5-ConstructionDesignCoordination@dot.state.fl.us
Construction Field Office Representative:
|  | Lauren Giarmo (Brevard County) | [10 empty] | lauren.giarmo@dot.state.fl.us
|  | Wilkes Kemp (Brevard County) | [10 empty] | wilkes.kemp@dot.state.fl.us
|  | Robert Marcoux (Brevard County) | [10 empty] | robert.marcoux@dot.state.fl.us
|  | Lindsay Robert (Brevard County) | [10 empty] | lindsay.roberts@dot.state.fl.us
|  | Rohan McDonald (Lake & Sumter County) | [10 empty] | rohan.mcdonald@dot.state.fl.us
|  | Eric Jaggers (Lake & Sumter County) | [10 empty] | eric.jaggers@dot.state.fl.us
|  | Kenneth Campbell (Marion County) | [10 empty] | kenneth.campbelljr@dot.state.fl.us
|  | Denise Larkin (Marion County) | [10 empty] | denise.larkin@dot.state.fl.us
|  | Preston Serpa (Marion County) | [10 empty] | preston.serpa@dot.state.fl.us
|  | Ryan Flipse (Orange & Osceola County) | [10 empty] | ryan.flipse@dot.state.fl.us
|  | Uvendra Gopal (Ray) (Orange & Osceola County) | [10 empty] | uvendra.gopal@dot.state.fl.us
|  | Tushar Patel (Orange, Osceola & Seminole County) | [10 empty] | tushar.patel@dot.state.fl.us
|  | Joshua Kelly (Orange, Osceola & Seminole County) | [10 empty] | Joshua.kelly@oz-matic.com
|  | Tammie Andrews (Seminole County) | [10 empty] | tammie.andrews@dot.state.fl.us
|  | Alexander Mackey (Volusia & Flager County) | [10 empty] | alexander.mackey@dot.state.fl.us
|  | Christopher Engels (Volusia & Flager County) | [10 empty] | christopher.engels@dot.state.fl.us
|  | Rey Diaz (District/ERC Submittals) | [10 empty] | rey.diaz@dot.state.fl.us
|  | Helena Ly (District/ERC Submittals) | [10 empty] | helena.ly@dot.state.fl.us
|  | Kenneth Tomory (District/ERC Submittals) | [10 empty] | kenneth.tomory@dot.state.fl.us
|  | Denise Druding (Volusia & Flager County) | [10 empty] | denise.druding@dot.state.fl.us
Others (as needed):
Minutes of meeting will be emailed by:
Revised pavement design will be submitted by:
* If Black Base is recommended, Please CC: D5-SpecPhase@dot.state.fl.us in Meeting Minutes Distribution

## Operation Center
County | Operation Center | People
Brevard | Brevard | Esther Montoya Wilkes Kemp Lindsay Roberts
Volusia & Flager | Deland | Dwight Grube Denise Druding
Lake & Sumter | Leesburg | Rohan McDonald Eric jaggers
Marion | Ocala | Kenneth Campbell Denise Larkin
Orange & Osceola | Orlando | Ryan Flipse Ray Gopal Josh Kelly
Seminole | Oviedo | Tammie Andrews Jonathan Duazo Josh Kelly?

## Counties (hidden)
Please select county
Brevard
Flagler
Lake
Marion
Orange
Osceola
Seminole
Sumter
Volusia